MandE NEWS: Progress and Financial Report

January 1st to December 31st 2004

By Rick Davies, Editor/Manager, MandE NEWS, Tuesday, Tuesday, 01 February 2005

Please note: The Progress Report for the previous two years (2002 & 2003) can be found at http://www.mande.co.uk/docs/MandENEWS2002progressreport.doc

http://www.mande.co.uk/docs/MandENEWS2003progressreport.doc

1. Changes in Funding Support

- There have been no changes in the numbers of donors supporting MandE NEWS in this last calendar year. As in late 2004, there are still 10 organisations funding MandE NEWS, nine of which are UK based NGOs (Oxfam, Save the Children, ActionAid, Christian Aid, CAFOD, CIIR, World Vision, WWF, and Exchange). IDRC (Canada) is the tenth donor.

- 2004 is the last of a three-year period of funding provided by these agencies, via the offices of BOND, UK. A funding proposal will now be developed and submitted to these donors for a further period of three years, from 2005 to 2007.

2. Achievements

This section covers all the performance measures listed in the 2001-2004 proposal, and the 2002 and 2003 Progress Reports. The overall ideal is to increase performance on each measure, year by year.

2.1 MandE NEWS continues to achieve wide recognition on the internet.

- When the words "monitoring and evaluation" are typed into Google, MandE NEWS appears on the top of the first page of results, which includes a total of 15,100,000 possibly relevant websites (It appears third on the first page when "and" is omitted). This compares to being first amongst 3,540,000 in January 2004 and 2,090,000 in January 2002. Google is the most widely used Internet search engine. In 2004 it accounted for 76% of all search engine referrals

- However, when "monitoring" or "evaluation" are typed into Google separately MandE NEWS is less prominent. It appears on the 13th page when "monitoring" is the search word, and the 20th page when "evaluation is the search word, versus 10th and 15th pages in January 2004.

- A growing number of websites have links to MandE NEWS, although the evidence is somewhat contradictory. When Google is asked to " Find web pages that link to www.mande.co.uk" it reports a total of 247, versus 170 in January 2004. When Google is asked to " Find web pages that contain the term "www.mande.co.uk" it reports 2,610 websites versus 681 in January 2004.

2.2 The number of visitors to MandE NEWS is growing

- The highest monthly number of visitors was 2,634 in November 2004. This represents a 12 increase on 2347 in April 2003, the highest level that year. That peak is thought to have been due to the publication of the results of the online and email surveys of users of the MandE NEWS. Visit numbers were much higher in the week after the survey report was uploaded.

- The upward trend in visitor numbers over the last 20 months is shown below. The 2003 months are understated because there was a mirror version of the home page in existence until December 2003, which also attracted traffic. Removal of that version led to a drop in visits in early 2004.

2.3 The mailing list was transformed

- There were 1168 people on the email update mailing list as of December 31st 2003. By June this year the list had grown to around 1300 people. However, the mailing list was a one way form of communication and being used infrequently, only two or three times a year, and only by the Editor

- In June 2004 members of this list were emailed and asked if they would like to join a new MandE NEWS mailing list that would enable communication between members, or simply receipt of notices from the Editor, as they wished. Their active consent was required before their email addresses could be used on a Yahoo based egroup. Approximately 210 people did so, being approximately 16% of the old mailing list.

- Since then around 30 people per month have joined the mailing list. This represents an increase on the 20 to 25 per month who were joining the previous mailing list in 2003. There were 380 members by late January 2005.

- The mailing list is now 46% larger than the Xceval mailing list, the most comparable email list dealing with monitoring and evaluation in an international setting

- 220 messages have been posted on the new mailing list, approximately 36 a month. The largest numbers were posted in the first month, when the new list was first established.

- Drop-out rates are low. Twelve members have dropped out since July 2004. All have returned simple three-question questionnaires as to why they have left.

- The Editor also facilitates three other M&E mailing lists, whose details are available via http://groups.yahoo.com/group/MandENEWS/

- REMAPP: A UK NGO M&E group that started in the early 1990's. 103 members

- "Most Significant Changes" mailing list: This is focused on the MSC method of monitoring-without-indicators,  and has 219 members

- Network Evaluation mailing list, with 39 members

2.4 The range of countries accessing MandE NEWS has grown

- Visits were recorded from 131 countries, versus 132, in 2003, 105 in 2002 and 106 in 2001.

- 54% of visitors come from unknown locations. Amongst the remaining 46% from known locations, 35% come from Europe and North America, and 11% from elsewhere. This figure has barely changed from 2003.

- An analysis of the small proportion of visitors who used the Opinion Poll shows 59% from Europe and North America, and 41% from elsewhere.

- Amongst the 380 members of the MandE NEWS mailing list at the end of January 2005 the percentage of visitors who come from outside of Europe and North America is much higher, at an estimated 65%. This percentage is higher than the 2003 figure (53%).

2.5 The volume of information available on MandE NEWS continues to increase

- Two new sections were added to the site in 2004:

- An Editorial blog called Rick on the Road.

- Thirteen editorial comments have been posted since April 2004

- An M&E Training Providers page. There is a high demand for information about sources of M&E training.

- The Searchable Archives now hold more than 520 items, a few less than in 2003, after redundant items with non-functioning links were removed.

- There are now more than 526 postings on the Open Forum. The Open Forum has had 129 new postings since December 31st, 2003. The rate of postings (average of 11 per month) has been variable over the year and seems to be lower than 2003 when the average was 17 per month. However the number has increased in the last two months after the Open Forum was publicised on the MandE NEWS mailing list.

- The most popular area of the Open Forum, in terms of number of postings, are the M&E Vacancies, and Information Needed categories. The same was the case in 2003 and 2002.

- As of November 2004, the MandE NEWS home page currently features 45 items that are less than 6 months old. All items over 6 months in age are moved from the homepage to Archives. This number is up from the 31 items in late December 2003.

- The Visitors Links page has links to 93 other related websites, along with descriptions of those websites. These have all been contributed by visitors to the MandE NEWS website. 21 of these were added in 2004. This facility was used the most by NGOs and consultancy firms. This is consistent with findings from the user survey (see below).

2.6 The interactivity of the MandE NEWS website has been improved

- The most significant development has been the re-structuring of the MandE NEWS mailing list, as described above.

- "The Rick on the Road" blog has a "Comment" facility that visitors can use to comment on the Editorial postings. Only one has done so, so far.

- From August 2002 there has been an online opinion poll, visible on the top of the home page. The focus of this poll was on the visitors usage and views of the MandE NEWS website. A total of 75 people have used the poll, 18 in the last year. The results to date can be found at http://pub27.bravenet.com/vote/stats.php?usernum=2241665034

- An opinion survey was emailed out to 938 members of the MandE NEWS email update list in late December 2002. The survey report can also be found online at http://www.mande.co.uk/docs/emailsurveyreport.doc A new email survey will be sent out in mid-2005, to all the current members of the MandE NEWS mailing list

2.7 The transparency of the MandE NEWS website has been improved

- There is now a special section of the website where visitors can access copes of the 2001 funding proposal sent to MandE NEWS donors, and the 2002 and 2003 Progress and Financial Reports produced since then. These documents include budgets and expenditure reports. See http://www.mande.co.uk/ProgressReports.htm

3. Areas needing more attention

3.1 Increasing the volume of information available

- The contents of the Archives need editing, to repair broken links. Up to 10% of items have links that no longer function.

- More news items need to be solicited from the growing membership of the MandE NEWS mailing list

- The list of editorial items on the bottom of the home page needs to be completed

4. Financial report

- The total expenditure for the 2004 year was £7,779.28. This figure is broken down in the table in Annex 1 (next page), next to the original budgeted amounts for each expense category. The expenses relate to a not-quite-calendar year, because funding was provided from 1st November 2001.

- I have submitted an invoice this month to BOND for the above amount, spent on the management of MandE NEWS in 2004. BOND in turn will be seeking any grants still due for 2004 from the 10 donors to MandE NEWS.

- It is expected that a small surplus may remain from the grants given in support of the 2001 proposal. If so, permission will be sought form donors to continue funding of MandE NEWS on a pro rata basis, until those remaining funds have been used.

Annex 1: Budgeted annual costs for 2003-2004 and actual costs

| Annual costs | Budgeted | Actual |
| --- | --- | --- |
| Items | Description | 1/11/03 to 31/10/04 |
| 1. | Expenses |  |  |
| 1.1 | Hosting of web site by Demon @ £20 per month Vat component included | 240.00 | 282.00 |
| 1.2 | Internet call charges @ £24.99 per month via NTL Additional charges levied by NTL since 15/4/02 | 143.88 | 299.88 |
| 1.3 | Software upgrades and additions Extreme tracking - monthly charge $5.00 LinkAlarm annual fee $71.28 | 150.00 | 33.25 5.53 |
| 1.4 | Incidentals (stationery, p/copy, postage) | 50.00 | 0.00 |
|  | Sub-total | 583.88 | 620.66 |
|  | VAT on above @17.5% | 102.18 | 108.62 |
| 2. | Consultancy time |  |  |
| 2.1 | Site management: R Davies, @£250 per day x 2 days per month | 6,000.00 | 6,000.00 |
| 2.2 | Technical support, from 3rd parties, as needed | 1,000.00 | 0.00 |
|  | Sub-total | 7,000.00 | 6,000.00 |
|  | VAT on above @17.5% | 1,225.00 | 1,050.00 |
|  | Items 1 & 2 Sub-total | 7,583.88 | 7,620.66 |
|  | Including VAT | 8,911.06 | 7,779.28 |
| 3. | BOND management fee | 758.38 | 762.06 |
|  | (10% of items 1&2) (not including VAT) |  |  |

Annex 2: The current structure of MandE NEWS, as of early 2005

# Footnotes

See http://www.useit.com/about/searchreferrals.html

Unique visitors, being visitors coming from computers with different addresses on any one day. This use of this measure neglects the possibility that more than one person may use a computer at one site to access MandE NEWS.

See http://home.wmis.net/~russon/icce/